UNIVERSITY OF AGRICULTURE, FAISALABAD

Faculty of Social Sciences

Director,

Office of Research, Innovation

& Commercialization,

University of Agriculture, Faisalabad

Through: Proper Channel

Subject: Submission of Research Proposal to EFS UAF

With reference to call for proposal on Technology Transfer and Product Commercialization by Endowment Fund Secretariat, University of Agriculture, Faisalabad, I hereby submit six (6) hard copies of a project proposal entitled" Technology transfer through Print Media" for further necessary action and transmission to the concerned quarter please. An advance soft copy has already been sent to EFS.

Dr. M. Iqbal Zafar

Professor/Convener, Zarai Digest,

Faculty of Social Sciences,

University of Agriculture, Faisalabad

Pakistan

Encl.

- Complete project proposal

- Detail of special numbers of Zarai Digest along with their number of copies to be published

- Budget estimates by University Press for printing of 11000 copies of special numbers of Zarai Digest

GUIDELINES FOR THE COMPLETION OF COMPLETE PROJECT PROPOSAL (ANNEXURE TT-B)

(Submit 6 hard copies along with a soft copy)

Annexure TT-B

|  | ## UNIVERSITY OF AGRICULTURE, FAISALABAD, PAKISTAN UAF-US COLLABORATION FOR STRENGTHENING OF AGRI. ACADEMIA Phone: 041-9201125, 9200161-170, Ext. 3604, 3607, Fax: 041-9201333 Email: efs@uaf.edu.pk |
| --- | --- |

Proposal Identification No

(To be allotted by UAF)

COMPLETE PROJECT PROPOSAL

1.   Project Title:

Technology transfer through Print Media

2.   Applicant's Details:

- Principal Investigator:

Name: 			Dr. M. Iqbal Zafar

Qualification:		PhD

Institution/Organization: 	University of Agriculture, Faisalabad

Present Position: 		Professor/Convener, Zarai Digest Advisory and 						Management Board, UAF

Status (Regular/Adhoc/Contract): Regular

Postal Address: 		Dean, Faculty of Social Sciences, University of 						Agriculture, Faisalabad

Telephone: +92-41-9200196  Mobile: 03216440321	E-mail: drmizafar@hotmail.com

- Co-Principal Investigator:________________________________________

Name: 			Dr. Shoukat Ali

Qualification:		PhD

Institution/Organization: 	University of Agriculture, Faisalabad

Present Position: 	Assistant Professor/Editor, Zarai Digest/Secretary, Zarai Digest Advisory and Management Board, UAF

Status (Regular/Adhoc/Contract): 	Regular/TTS

Postal Address: 	Institute of Agri. Extension & Rural Development, 	Faculty of Social Sciences, University of Agriculture, Faisalabad

- Team members:________________________________________

- Prof. Dr. Tanvir Ali

- Prof. Dr. Jilal Arif, Principle Officer (PRP)

- Dr. Muzhar Hussain Ranjha

d. Other Staff members

- Khalid Saleem Khan

- Muhammad Ismail

3. Overseas cooperating Scientist/Organization:

4.  Total Cost (Rs. Million): 	1.83 million

5.  Project Location:	Zarai Digest Publications, University of Agriculture Faisalabad

6.  Project Duration (months): 18 months

7. GENERAL

a) What is Existing Situation?

Zarai Digest Publications is an important organ of University of Agri. Faisalabad and is performing a significant role in the transfer of modern agricultural technology and information through print media by publishing regular and special issues of Zarii Digest. It publishes agri. innovations and technology in a simple and understandable Urdu language for the promotion of agriculture, cottage industry, livestock, poultry and allied fields of agriculture.

ZDP participate and display the publications in Kisan Melas, Agri. exhibitions, seminars and conferences of national and international levels so that the farmers may get published agri. material. It also provides the publications on the farmers door step on a simple letter or call by the farmers.

Zarai Digest Publications intends to publish 11 special numbers of the Zaria digest (please see annexure-I) which have great demand among the farming community. These special numbers will play an important and significant role in disseminating latest agricultural technologies among farmers. The literacy rate in Pakistan is getting higher and higher. In a situation where farmers are not literate, their sons and daughters are literate one. They can receive agricultural information through Zarai Digest and translate it for their parents. The published information remains permanent record with the farming family which can be consulted at any time as and when required. This project has therefore been designed to diffuse agri. information among farm families through print media i.e. Zarai Diest Special Numbers.

Literature review of similar work

A lot of literature is available concerning the significance of print media in the diffusion of agri. information.

b) What are the scope and issues to be addressed and your approach to address them?

All information required by the farm families concerning plant and crop, livestock management, veterinary sciences, farm machinery, social issues and economic concerns will be provided to them through the new and revised publications of Zarai Digest’s Special Numbers. This project will also provide an opportunity to the UAF scientist to share their expertise with the farmers through print media.

- Give Justification of the project.

The average yields of crops, horticultural plants and production of livestock/poultry is very low as compared to their potential yield/ production. The main reason for low productivity is lack of timely availability of agri. information on the part of farmers. This project will ensure the availability of latest information to the famers in an interesting and understandable form.

8.  THE TECHNOLOGY

a) Give brief overview of the Technology to be transferred

All technologies required by the farmers

b) Have you practically tested these methods earlier? If, yes, where?

Yes, at UAF

9.  OBJECTIVES:

To:

- Write and publish new special numbers of ZD.

- Revise and publish already existed numbers of ZD.

- To disseminate latest agri. information among farmers through agri. exhibitions and other services at the door step of the farmers.

10. PROCEDURES

a) Methodology, Quantitative and Qualitative parameters along with time frame to gauge the effects of your intervention?

- The authors for writing new ZD special numbers will be identified and requested to write Special Numbers. The draft will be peer reviewed prior to the editing, designing and publication.

- The authors of already existed ZD special numbers will be requested to update and revise the Numbers. The draft will be peer reviewed prior to the editing, designing and publication.

- The published material will be offered to the farmers on nominal prices.

b) Time frame and modes of documenting different steps of implementation and achievements of the project?

- 8 months for writing and updating Special numbers

- 3 month for composing special numbers

- 3 months for peer review

- 2 months for editing and designing

- 2 months for publications

11. PLAN OF WORK:

a) Activities:

| Year |  | Activities | Location | Researcher responsible |
| --- | --- | --- | --- | --- |
| 1 | 1st half (9 months) | Writing, updating and peer review of special numbers | UAF | Dr. Muhammad Iqbal Zafar & Dr. Shoukat Ali |
| 2 | 2nd half (9 months) | Editing, designing and publications of special numbers | UAF | Dr. Muhammad Iqbal Zafar & Dr. Shoukat Ali |

b) Schedule of activities in form of a chart (Annexure I).

12. State if the project has been submitted to any other Funding agency for financial support. If so, with what results?

No_____________________________________________________________________

13. No of projects being run by:

a)	PI (CV Attached)

b)	Co-PI

| Project title and duration (from-to) | Status as PI or Co-PI | Funding Agency | Budget | Status |
| --- | --- | --- | --- | --- |
| Formulating research based agricultural extension policy guidelines through participatory approach in the Punjab, Pakistan | PI | HEC | 1.5 million | In progress |
| Technology transfer through cyber extension: helping communities to help themselves | Team member | EFS, UAF |  | In progress |
| Creating knowledge based society through agricultural technology transfer via FM Radio | Team member | EFS, UAF |  | In progress |
| Gender empowerment and home life improvement of rural poor through appropriate technology transfer | Team member | EFS, UAF | 1.768 million | Completed |

CV attached

14. Budget Summary:

(Rs. millions)

| Sr. # | #### OBJECT | Months (18) | TOTAL |
| --- | --- | --- | --- |
| 1 | #### Operating Expenses | 1.54775 | 1.54775 |
| 2 | Capital Expenses | 0.2625 | 0.2625 |
| 3 | #### Admin and Audit/Accounts Fee* | 0.0217 | 0.0217 |
|  | Total | 1.83195 | 1.83195 |

*Admin and Audit/Accounts Fee: will be worked out as 2% of the operational expenses excluding honoraria to PI and CO-PI

Note: After the completion of project, the fixed assets will be the property of UAF. However, the equipment, etc. might be allotted to participating/cooperating Institutions with fair justification.

## BUDGET DETAILS OF THE PROJECT

| A030a | Honorarium to PI | 0.135 |
| --- | --- | --- |
| A030b | Honorarium to Co-PI | 0.165 |
| A030 | Honoraria | 0.3 |
| A031 | TA/DA to Officers/Staff |  |
| A032a | Postage & Telegram |  |
| A032b | Telephone & Trunk Calls/Broad band internet charges |  |
| A032c | Running/Hiring Cost of Vehicles |  |
| A032d | Transportation of Goods | 0.02 |
| A032 | Communication | 0.02 |
| A033a | Utilities |  |
| A033b | Stationary | 0.02 |
| A033c | Printing & Publication | 0.775 |
| A033d | Rent of Land/Machinery/Office Building |  |
| A033e | Consumable Stores | 0.01 |
| A033 | Utilities/Office Support/Rent | 0.805 |
| A034a | Office Building |  |
| A034b | Equipment and Machinery |  |
| A034c | Computer & Office Equipment | 0.02 |
| A034d | Furniture & Fixture |  |
| A034e | Vehicles |  |
| A034 | Repair & Maintenance | 0.02 |
| A035a | Consultancy Services |  |
| A035b | Payment to Other Agencies (authors and reviewers) | 0.09 |
| A035c | Contractual Services (skilled & unskilled) | 0.1 |
| A035 | Other Services | 0.19 |
| A036a | Seminar/workshop/media conference |  |
| A036b | Foreign Delegation/Collaborating Scientist's visit |  |
| A036c | Delegation Abroad Preferably to the Institute of Collaborating Scientist |  |
| A036d | Fellowship/Stipend |  |
| A036e | Technology Transfer/farmers days and demo/exhibitions | 0.05 |
| A036f | Miscellaneous (not more than 1% of operational cost) |  |
| A036 | Other Expenses | 0.05 |
|  | SUB TOTAL (Operational Cost except Honorarium) | 1.085 |
|  | (Sum of A031 to A036) |  |
| A037 | Support to Host Institutes (Overhead charges) (15% of Sub Total above) | 0.16275 |
| A038 | OPERATIONAL EXPENSES (Sum of A030 to A037) | 1.54775 |
| A039a | Equipment & Machinery (server, storage, EDH) |  |
| A039b | Computer & Office Equipment (laptop, computer and printer) | 0.25 |
| A039c | Furniture & Fixture |  |
| A039d | Other assets |  |
| A039e | Escalation coverage (not more than 5% of capital expenses) | 0.0125 |
| A039 | CAPITAL EXPENSES | 0.2625 |
|  | TOTAL COST (A038 + A039 ) | 1.81025 |
| A040 | Admin and Audit/Accounts Fee (2% of Operational Expenses excluding honoraria) | 0.0217 |
|  | GRAND TOTAL | 1.83195 |
|  | (Total cost + Audit/Accounts fee) |  |

LIST OF CAPITAL ITEMS

| Head | Item with Specifications | Rate | Quantity | Amount (Rs) |
| --- | --- | --- | --- | --- |
| A039a | Equipment and Machinery |  |  |  |
|  | NA | NA | NA | NA |
|  | NA | NA | NA | NA |
|  | NA | NA | NA | NA |
| Sub-total |  |  |  | 250000 |
| A039b | Computer & Office Equipment |  |  |  |
| 1 | Laptop | 90000 | 1 | 90000 |
| 2 | Computer | 65000 | 1 | 65000 |
| 3 | Printer (3 in one) | 45000 | 1 | 45000 |
| Sub-total |  |  |  |  |
| A039c | Furniture & Fixtures |  |  |  |
|  | NA | NA | NA | NA |
|  | NA | NA | NA | NA |
|  | NA | NA | NA | NA |
|  | NA | NA | NA | NA |
|  | Sub-total |  |  |  |
| GRAND TOTAL |  |  |  | 250000 |

15. Certification:

It is certified that the above information is accurate and the proposal will be executed in accordance with the agreement with UAF. That I will complete the proposed work plan and the results/ outcomes of the project will be shared with UAF.

| Principal Investigator Name: ______________________ ______________________ (Seal and Signature) Date: ______________________ | Co-Principal Investigator Name: _____________________ _____________________ (Seal and Signature) Date: _____________________ |
| --- | --- |

16. Endorsement

It is certified that this proposal has the concurrence and support of Head of Institution/Organization

______________________________________

(Seal and Signature)

Date: __________________________________

Director, ORIC

_______________________________________

(Seal and Signature)

Date: __________________________________

Annexure I

SCHEDULE OF ACTIVITIES

| Sr. # | Activities | Months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 1 | Team formation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Write up and revision of special numbers of the digest |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Composing of the numbers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Peer review of the numbers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Editing and designing of the numbers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Printing of the digest |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

6